## Seguimiento
ID de acción | Categoría | Título | Prioridad | Rol sugerido | Por qué ahora | Siguiente paso recomendado | Importe relacionado (MXN) | IDs de fuente | Evidencia de origen | Snapshot de origen | Responsable | Estado | Fecha objetivo | Nota de revisión | Evidencia del resultado
servicio-742dc2b7d30e74a7 | servicio | Revisar compromiso vencido · ORD-002 | P1 | Jefatura de taller | La orden sigue abierta después de la fecha prometida. | Confirmar el avance físico, la causa del atraso y el responsable. Registrar una fecha de revisión sin prometer una entrega no validada. |  | ["ORD-002"] | [{"field":"status","record_id":"ORD-002","snapshot_id":"demo-semana-02","table":"orders","value":"in_service"},{"field":"received_at","record_id":"ORD-002","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-12T12:00:00Z"},{"field":"promised_at","record_id":"ORD-002","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-18T12:00:00Z"},{"field":"delivered_at","record_id":"ORD-002","snapshot_id":"demo-semana-02","table":"orders","value":null},{"field":"block_reason","record_id":"ORD-002","snapshot_id":"demo-semana-02","table":"orders","value":null},{"field":"technician_ref","record_id":"ORD-002","snapshot_id":"demo-semana-02","table":"orders","value":"TECH-02"}] | demo-semana-02 |  | pending
cartera-f8edcf6127e8ad7d | cartera | Revisar saldo vencido · INV-001 | P2 | Administración | Saldo documentado con 9 días calendario de atraso; 2 pagos vinculados. | Conciliar los pagos con la fuente y confirmar si existe disputa o acuerdo vigente. Registrar el siguiente paso autorizado y su fecha. | 600 | ["INV-001"] | [{"field":"amount_cents","record_id":"INV-001","snapshot_id":"demo-semana-02","table":"invoices","value":150000},{"field":"issued_at","record_id":"INV-001","snapshot_id":"demo-semana-02","table":"invoices","value":"2026-09-13T12:00:00Z"},{"field":"due_at","record_id":"INV-001","snapshot_id":"demo-semana-02","table":"invoices","value":"2026-09-20T12:00:00Z"},{"field":"status","record_id":"INV-001","snapshot_id":"demo-semana-02","table":"invoices","value":"issued"},{"field":"invoice_id","record_id":"PAY-001","snapshot_id":"demo-semana-02","table":"payments","value":"INV-001"},{"field":"amount_cents","record_id":"PAY-001","snapshot_id":"demo-semana-02","table":"payments","value":50000},{"field":"paid_at","record_id":"PAY-001","snapshot_id":"demo-semana-02","table":"payments","value":"2026-09-21T12:00:00Z"},{"field":"invoice_id","record_id":"PAY-003","snapshot_id":"demo-semana-02","table":"payments","value":"INV-001"},{"field":"amount_cents","record_id":"PAY-003","snapshot_id":"demo-semana-02","table":"payments","value":40000},{"field":"paid_at","record_id":"PAY-003","snapshot_id":"demo-semana-02","table":"payments","value":"2026-09-24T12:00:00Z"}] | demo-semana-02 |  | pending
facturacion-04c3834e2cba4e89 | facturacion | Conciliar servicio entregado · ORD-004 | P2 | Administración | No hay factura vigente vinculada en los datos recibidos; esto no prueba falta de facturación. | Buscar la factura o documentar garantía, cortesía o cobertura del contrato. Completar el vínculo sin estimar ingresos. |  | ["ORD-004"] | [{"field":"status","record_id":"ORD-004","snapshot_id":"demo-semana-02","table":"orders","value":"delivered"},{"field":"received_at","record_id":"ORD-004","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-07T12:00:00Z"},{"field":"promised_at","record_id":"ORD-004","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-12T12:00:00Z"},{"field":"delivered_at","record_id":"ORD-004","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-15T12:00:00Z"},{"field":"block_reason","record_id":"ORD-004","snapshot_id":"demo-semana-02","table":"orders","value":null},{"field":"technician_ref","record_id":"ORD-004","snapshot_id":"demo-semana-02","table":"orders","value":"TECH-03"}] | demo-semana-02 |  | pending
facturacion-e0fb4f2947b66a33 | facturacion | Conciliar servicio entregado · ORD-003 | P2 | Administración | No hay factura vigente vinculada en los datos recibidos; esto no prueba falta de facturación. | Buscar la factura o documentar garantía, cortesía o cobertura del contrato. Completar el vínculo sin estimar ingresos. |  | ["ORD-003"] | [{"field":"status","record_id":"ORD-003","snapshot_id":"demo-semana-02","table":"orders","value":"delivered"},{"field":"received_at","record_id":"ORD-003","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-13T12:00:00Z"},{"field":"promised_at","record_id":"ORD-003","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-20T12:00:00Z"},{"field":"delivered_at","record_id":"ORD-003","snapshot_id":"demo-semana-02","table":"orders","value":"2026-09-26T18:00:00Z"},{"field":"block_reason","record_id":"ORD-003","snapshot_id":"demo-semana-02","table":"orders","value":null},{"field":"technician_ref","record_id":"ORD-003","snapshot_id":"demo-semana-02","table":"orders","value":"TECH-01"}] | demo-semana-02 |  | pending

## Instrucciones
MILENIO / Seguimiento de acciones
Libro local para que una persona registre el seguimiento de decisiones con evidencia. Los datos son sintéticos y se refieren exclusivamente al corte indicado.
snapshot_id | demo-semana-02
as_of | 2026-09-29T18:00:00Z
synthetic | true
Qué se puede editar | Responsable, Estado, Fecha objetivo, Nota de revisión y Evidencia del resultado en la hoja Seguimiento.
Qué no se puede editar | La sección de origen se conserva para auditoría. Los campos técnicos de IDs, evidencia, snapshot e importe relacionado no deben cambiarse; si no coinciden con el origen, la importación se rechaza.
Contexto de origen | El motivo, el siguiente paso y la evidencia completa también aparecen en INICIO.html y Gerencia.xlsx. Las columnas de origen de Seguimiento están ocultas para facilitar la reunión; puede mostrarlas cuando necesite auditar el vínculo.
Para marcar done | Escriba Responsable, Nota de revisión y Evidencia del resultado. El resultado es auto-reportado; la hoja no prueba por sí sola el resultado del negocio.
Estados permitidos | Use los códigos: pending = pendiente; accepted = aceptada; in_progress = en curso; done = cerrada con evidencia; dismissed = descartada. accepted e in_progress requieren responsable y fecha objetivo; dismissed requiere nota.
Límite operativo | Este libro no contacta clientes, no cambia un CRM, no agenda, no cobra, no compra y no publica. Toda acción de negocio requiere un proceso humano separado.
Auditoría | Conserve el snapshot original. El registro JSONL de importación debe incluir un identificador de fuente y un revisor declarado por quien lo registra; esa etiqueta es auto-reportada y no verifica una identidad.